## Supervisor
Date / Time | Venue | Attendees | Agenda Items | Decisions/Directions | Remarks/Progress | Week's Evaluation (filled by Supervisor)
2017-09-14 | Sir Rauf's room | Tabish, Sarim , Ali | Discussion of idea for FYP | To find the related research papers and find the uniqueness of the project | Completed
2017-09-18 | Sir Rauf's room | Tabish, Sarim , Ali | What and how to get Twitter data | API’s twitter provides for extracting tweets. | Completed
2017-10-05 | Sir Rauf's room | Tabish, Ali | Progress of twitter tweets | Be focused and keep limited and recent tweets in the database | Progress
2017-10-12 | Sir Rauf's room | Tabish, Ali | Twitter tweet,application feature | To extract the tweets from the authentic channels of twitter. | Continuous process
2017-10-19 | Sir Rauf's room | Tabish, Sarim , Ali | Android Interface | To verify the implementation methods and design of the interface.(web and android) | Completed
2017-11-02 | Sir Rauf's room | Tabish, Sarim , Ali | Progress | To Learn and Implement the layout of the appplication | Completed
2017-11-09 | Sir Rauf's room | Tabish, Sarim , Ali | Progress | To Learn and Implement the layout of the appplication. | Completed
2017-11-21 | Sir Rauf's room | Tabish, Sarim , Ali | Verification of the layout | To verify the layout and designing of the application. | Progress
2017-11-30 | Sir Rauf's room | Tabish, Ali | database design and web services for phase 1 | To implement the backend services of the application including database. | Completed
2017-12-07 | Sir Rauf's room | Tabish, Sarim , Ali | database design and web services for phase 1 | To implement the backend services of the application including database. | Completed

## Internal
Date / Time | Venue | Attendees | Agenda Items | Decisions/Directions | Remarks/Progress
2017-09-14 | Tabish House | Tabish, Ali , Sarim | To analyze the project idea | Understand the project individually
2017-09-15 | Tabsish House | Ali , Sarim , Tabish | To discuss and find the unique features of the project and understand the project domain. | Research about the existing traffic applications
2017-09-18 | Tabish House | Tabish, Ali , Sarim | Discussion about different modules of the project | Stay focused and break down the project goals.
2017-09-21 | Tabish House | Tabish, Ali , Sarim | divide the work load and focus on individual goals | start implementation
2017-09-25 | Tabish House | Tabish, Ali , Sarim | Project proposal | completion of proposal in progress
2017-09-26 | Tabish House | Tabish, Ali | Project proposal | proposal was submitted
2017-10-05 | Tabish House | Tabish, Ali | weak accept changes in the proposal recommended by jury | changes was made.
2017-10-12 | Ali House | Tabish, Ali | Add authentic twitter channels into list and work on the widget of twitter, learn about twitter API | Search and implement twitter api
2017-10-13 | Skype | Tabish, Sarim , Ali | discussion on twitter implementation | get some authentic channels and list them into the account to get news about the city.
2017-10-19 | Tabish House | Tabish, Ali | make Mid Jury evaluation PPT,To learn android and discover the layout of the application | PPT was submitted,Start udacity course to know basics of android
2017-10-21 | Skype | Tabish, Ali , Sarim | discussion about the progress of the project | work fast and achieve the goals.
2017-10-25 | Tabish House | Tabish, Ali | Requirement specification | document in progress
2017-10-26 | Tabish House | Tabish, Ali | Requirement specification | document submitted
2017-11-02 | Ali House | Tabish, Ali | Start the implementation of the application | learn and implement basic structure of application(android)
2017-11-07 | Ali House | Tabish, Ali , Sarim | Design specification | document in progress
2017-11-08 | Ali House | Tabish, Ali | Design specification | completed but not submitted
2017-11-09 | Tabish House | Tabish, Ali , Sarim | Start the implementation of the application | submit Design specification ,Moreover learn and implement basic structure of application(android)
2017-11-21 | Tabish House | Sarim,Tabish, Ali | Discussion and implementation of web/android app. | learn and implement web services
2017-11-30 | Ali House | Tabish, Ali | implementation of web services and databases | implementation of the databases
2017-12-07 | Tabish House | Tabish, Ali , Sarim | verify the database relationship and implementation of web-services. | fetch real time tweets from the database through web services and display them on the mobile and web
2017-12-11 | Tabsish House | Tabish ,Ali, Sarim | make Final jury evaluation PPT and update the document | ppt was sent and document was updated
2017-12-12 | Tabish House | Tabish ,Ali | discuss and Finalize the code (Final Testing) | everything is working properly while bugs are removed, tweets aren't encoded by JSON because of special characters in the tweets so we'll remove this bug later